## Sheet1
Priorty List - Workshop I Game - (PAPA)
| Tasks | Source | Assigned To | Completion | Completed By?
ESSENTIAL | Gameplay Tasks
| Player Movement | Make from scratch | Harmandeep Singh | Yes | 2024-07-06
| Player lookout mechanics | Make from scratch | Harmandeep Singh | Yes | 2024-07-06
| Breathing Mechanics | Make from scratch | Harmandeep Singh | Yes | 2024-07-07
| Player interactions mechanics | Make from scratch | Harmandeep Singh | Yes | 2024-07-07
| Ghost follow script | Make from scratch | Harmandeep Singh | Yes | 2024-07-08
| Fear level mechanics | Make from scratch | Gopi Velmurugan | Yes | 2024-07-08
| Sequence of events | Make from scratch | Gopi Velmurugan | Yes | 2024-07-13
| Haunted house Greyboxing | Make from scratch | Amrinder Kaur | Yes | 2024-07-13
| Choice based ending mechanics | Make from scratch | Gopi Velmurugan | Cut | 2024-07-14
| Pause Menu | Make from scratch | Amrinder Kaur | Yes | 2024-07-15
| Checkpoint Mechanics | Make from scratch | Gopi Velmurugan | Yes
| Main menu Manager | Make from scratch | Gopi Velmurugan | Yes | 2024-07-15
| User Interface | Make from scratch | Amrinder Kaur | Yes | 2024-07-15
Sound Design
| Suzie voiceover | Make from scratch | Gopi Velmurugan | Yes | 2024-07-15
| Amanda's voiceover | Make from scratch | Gopi Velmurugan | Cut | 2024-07-10
| Richard's voiceover | Make from scratch | Gopi Velmurugan | Yes | 2024-07-11
| SFX's | Make from scratch | Gopi Velmurugan | Yes | 2024-07-12
| BG music | Get it from asset store | Gopi Velmurugan | Yes | 2024-07-13
Richard's Room
| Bed | Get it from asset store | Amrinder Kaur | Cut | 2024-07-10
| Table | Get it from asset store | Harmandeep Singh | Cut | 2024-07-09
| Lamps | Get it from asset store | Amrinder Kaur | Yes | 2024-07-11
| Photographs | Make from scratch | Harmandeep Singh | Yes | 2024-07-09
| Casket | Make from scratch | Gopi Velmurugan | Yes | 2024-07-13
| Blood textures for walls | Make from scratch | Gopi Velmurugan | Cut | 2024-07-13
Amanda's Room
| Bed | Get it from asset store | Amrinder Kaur | Yes | 2024-07-12
| Table | Get it from asset store | Harmandeep Singh | Yes | 2024-07-10
| Photographs | Make from scratch | Harmandeep Singh | Yes | 2024-07-10
| Book shelf | Get it from asset store | Harmandeep Singh | Yes | 2024-07-11
| Lamps | Get it from asset store | Amrinder Kaur | Cut | 2024-07-12
| Diary | Make from scratch | Harmandeep Singh | Cut | 2024-07-12
| Poison | Make from scratch | Harmandeep Singh | Yes | 2024-07-12
Basement
| Table | Get it from asset store | Gopi Velmurugan | Yes | 2024-07-13
| Chemicals | Make from scratch | Amrinder Kaur | Cut | 2024-07-12
| Chains | Make from scratch | Amrinder Kaur | Cut | 2024-07-13
| Room assets | Make from scratch | Harmandeep Singh | Yes | 2024-07-11
OPTIONAL | Suzie's room
| Bed | Get it from asset store | Amrinder Kaur | Yes | 2024-07-13
| Table | Get it from asset store | Harmandeep Singh | Yes | 2024-07-11
| Photographs | Make from scratch | Harmandeep Singh | Yes | 2024-07-11
| Dolls | Make from scratch | Amrinder Kaur | Yes | 2024-07-12
| Lamps | Get it from asset store | Amrinder Kaur | Yes | 2024-07-12
| Decorations | Make from scratch | Amrinder Kaur | Yes | 2024-07-12
Add Character models and animation
| Suzie | Make from scratch | Harmandeep Singh | Yes | 2024-07-26
| Suzie's Mother (Amanda) | Make from scratch | Amrinder Kaur | Yes | 2024-07-26
| Suzi'e Father (Richard) | Make from scratch | Gopi Velmurugan | Yes | 2024-07-26
| Ghost | Make from scratch | Gopi Velmurugan | Yes | 2024-07-26
| Suzie's character animation | Make from scratch | Harmandeep Singh | Yes | 2024-07-26
| Amanda's character animation | Make from scratch | Amrinder Kaur | Yes | 2024-07-26
| Richard's character animation | Make from scratch | Gopi Velmurugan | Yes | 2024-07-26
WISHLIST | Add Living Room assets
| Old Tv | Get it from asset store | Harmandeep Singh | Yes | 2024-08-02
| Wooden Base and ceiling | Get it from asset store | Harmandeep Singh | Yes | 2024-08-03
| Sofas | Get it from asset store | Amrinder Kaur | Yes | 2024-08-02
| Lamps | Get it from asset store | Gopi Velmurugan | Cut | 2024-08-02
| Carpet | Get it from asset store | Harmandeep Singh | Cut | 2024-08-06
| Telephone | Get it from asset store | Harmandeep Singh | Cut | 2024-08-07
| Additional if required | Get it from asset store | Amrinder Kaur | Cut | 2024-08-08
Add Kitchen assets
| Kitchen utensils and accessories | Get it from asset store | Amrinder Kaur | Cut | 2024-08-02
| Cookwares | Get it from asset store | Gopi Velmurugan | Cut | 2024-08-06
| Cutleries | Get it from asset store | Amrinder Kaur | Cut | 2024-08-02
| Shelves | Get it from asset store | Amrinder Kaur | Cut | 2024-08-06
Extras
| Extra Cut scenes | Make from scratch | Amrinder Kaur | Yes | 2024-08-06
| Modes - (Easy, Medium, Hard) | Make from scratch | Gopi Velmurugan | Cut | 2024-08-07
| Rats in the basement | Make from scratch | Gopi Velmurugan | Cut | 2024-08-06